## Plan
Work Backwards Change Plan
Example values are filled in (packing line changeover). Replace the yellow cells with your own. Free from CI-AI Fusion Ltd.
1. THE WIN
We're changing (X) | how we do changeovers on Line 2
So that (the win, Y) | every shift gets more run time with less rushing
Win date | 2026-06-30
You'll see (Z, measurable) | changeovers at 25 minutes or less
Who benefits | Line 2 operators, shift leads, planner, maintenance
2. OUTCOMES THAT PROVE IT
Measure | Baseline | Target | Latest | On track?
Average changeover time | 48 min | 25 min
Changeovers done to the standard | 0% | 90%
Output lost to changeovers per week | 6 hrs | 3 hrs
3. MILESTONES, WORKED BACKWARDS (fill M4 first)
Milestone | PDCA stage | Short name (for the speech) | What done looks like | Start | Due | Owner | Measure | Who needs to say yes | Risk | Status (RAG) | Notes
M4 | Act / Standardise | lock it in as standard work | Standard changeover sheet used on every shift; owner per shift; reviewed weekly at the team huddle | 2026-06-03 | 2026-06-30 | Shift leads | 90% to standard | All 3 shift leads | Slips back on night shift
M3 | Check | check the results | Two weeks of times recorded vs 25 min target; sheet adjusted with operator ideas | 2026-05-20 | 2026-06-02 | Line lead | Avg time vs target | Planner (schedule) | Data not recorded
M2 | Do | trial a better sequence | Trial the new sequence on one product family; prepare parts before the line stops | 2026-05-06 | 2026-05-19 | Line 2 team | Time per trial | Operators on trial | Seen as 'speed-up' | A
M1 | Plan | measure today's changeover together | Video and time 3 changeovers; team lists the steps; baseline agreed | 2026-04-22 | 2026-05-05 | Change lead | Baseline 48 min | Operators & maintenance | Team not consulted | G
R = off track, needs help · A = at risk · G = on track
4. PEOPLE SIDE
Who's affected | Line 2 operators (3 shifts), maintenance
Likely resistance | "This is a speed-up", "we tried this before"
How we involve them | Operators film and time it, choose the trial, own the sheet. Need help? The People Whisperer mentoring.
5. ELEVATOR SPEECH (built from your inputs)
6. FIRST ACTION TODAY (Houston step 5)
The 1 thing | Ask the night shift lead for 10 minutes at tomorrow's huddle to explain the idea and ask what slows changeovers down.

## Timeline
Timeline (weekly). Bars fill from each milestone's Start and Due dates on the Plan sheet
Week starting
Win date
Plan → Do → Check → Act runs forwards in time, but you planned it backwards from the win.

## How to use
How to use the Work Backwards Change Plan
1. Work backwards: start with THE WIN (Plan sheet, rows 5 to 9). What does success look like, by when, and who benefits?
2. Add 2 to 3 OUTCOMES that prove it, with today's baseline and a target. Update 'Latest' as you go.
3. Fill the MILESTONES from M4 (Act: it sticks) back to M1 (Plan). For each, ask: what has to be true before this can happen?
4. Give each milestone a start, a due date, an owner, a measure, who needs to say yes, and the main risk.
5. Set Status each week: G on track, A at risk, R off track. The cell colours itself.
6. The Timeline sheet draws the bars from your dates automatically. The WIN marker shows the win date.
7. Your ELEVATOR SPEECH (row 31) builds itself from your inputs. Read it aloud: aim for 30 seconds or less.
8. Fill the PEOPLE SIDE honestly. Team not buying in? Look at The People Whisperer mentoring on the Lead the Change page.
9. Finish with the FIRST ACTION TODAY, the same as Houston step 5, and log it in your Wins Log.
10. Coaching clients: we build this plan together across the 4 sessions of 'Lead your first improvement'.
Free from CI-AI Fusion Ltd · ci-ai-fusion.netlify.app/lead-the-change/#work-backwards