|  | Work Backwards Change Plan Start with the win, then work back to 4 PDCA milestones and a 30-second elevator speech. |
| --- | --- |

Change: ____________________________________   Change lead: ____________________   Date: __________

1  THE WIN (END GAME)   What success looks like, measurable outcome + date, who benefits

| The win |  |
| --- | --- |
| Who benefits |  |

2  OUTCOMES THAT PROVE IT   2 to 3 measures, baseline → target

| Measure | Baseline (today) | Target (by the win date) |
| --- | --- | --- |

3  MILESTONES, WORKED BACKWARDS   Fill M4 first, then M3, M2, M1. Each one makes the next possible

| Milestone | What done looks like | Date | Owner | Measure | Who needs to say yes | Risk |
| --- | --- | --- | --- | --- | --- | --- |
| M4 ACT Standardise: it sticks. Standard work, owners, habits |  |  |  |  |  |  |
| M3 CHECK Results measured against target, adjust |  |  |  |  |  |  |
| M2 DO Pilot or trial with the team, small wins |  |  |  |  |  |  |
| M1 PLAN Problem defined, team involved, baseline |  |  |  |  |  |  |

← work backwards from the win:  WIN  ←  M4 Act  ←  M3 Check  ←  M2 Do  ←  M1 Plan   (you'll do them forwards: Plan → Do → Check → Act)

4  PEOPLE SIDE   Who's affected, likely resistance, how we involve them

Affected: Likely resistance: How we involve them: Team not buying in? The People Whisperer mentoring can help: ci-ai-fusion.netlify.app/lead-the-change/#people-whisperer

5  ELEVATOR SPEECH   30 seconds or less, 3 parts

① We're changing ________________________ so that ________________________________ (the win). ② We'll get there in 4 steps: ____________, ____________, ____________, ____________. ③ By ______________ you'll see ________________________________.

6  FIRST ACTION TODAY   Same as Houston step 5: one thing today, then log it in your Wins Log

By when: ____________ Logged in Wins Log: ☐

Free resource from CI-AI Fusion Ltd · Lead the Change · ci-ai-fusion.netlify.app/lead-the-change/#work-backwards · Pairs with the Houston method worksheet (first action) and the Excel tracker.

|  | Work Backwards Change Plan: worked example Start with the win, then work back to 4 PDCA milestones and a 30-second elevator speech. |
| --- | --- |

Example only: a generic packing line. Replace with your own change.

1  THE WIN (END GAME)   What success looks like, measurable outcome + date, who benefits

| The win | Changeovers on Packing Line 2 take 25 minutes or less, every shift, by 30 June. Operators, shift leads and planning benefit: less rushing, more run time. |
| --- | --- |
| Who benefits | Line 2 operators, shift leads, planner, maintenance |

2  OUTCOMES THAT PROVE IT   2 to 3 measures, baseline → target

| Measure | Baseline (today) | Target (by the win date) |
| --- | --- | --- |
| Average changeover time | 48 min | 25 min |
| Changeovers done to the standard | 0% | 90% |
| Output lost to changeovers per week | 6 hrs | 3 hrs |

3  MILESTONES, WORKED BACKWARDS   Fill M4 first, then M3, M2, M1. Each one makes the next possible

| Milestone | What done looks like | Date | Owner | Measure | Who needs to say yes | Risk |
| --- | --- | --- | --- | --- | --- | --- |
| M4 ACT Standardise: it sticks. Standard work, owners, habits | Standard changeover sheet used on every shift; owner per shift; reviewed weekly at the team huddle | 30 Jun | Shift leads | 90% to standard | All 3 shift leads | Slips back on night shift |
| M3 CHECK Results measured against target, adjust | Two weeks of times recorded vs 25 min target; sheet adjusted with operator ideas | 2 Jun | Line lead | Avg time vs target | Planner (schedule) | Data not recorded |
| M2 DO Pilot or trial with the team, small wins | Trial the new sequence on one product family; prepare parts before the line stops | 19 May | Line 2 team | Time per trial | Operators on trial | Seen as 'speed-up' |
| M1 PLAN Problem defined, team involved, baseline | Video and time 3 changeovers; team lists the steps; baseline agreed | 5 May | Change lead | Baseline 48 min | Operators & maintenance | Team not consulted |

← work backwards from the win:  WIN  ←  M4 Act  ←  M3 Check  ←  M2 Do  ←  M1 Plan   (you'll do them forwards: Plan → Do → Check → Act)

4  PEOPLE SIDE   Who's affected, likely resistance, how we involve them

Affected: operators on all 3 shifts, maintenance. Likely resistance: "this is a speed-up", "we tried this before". Involve: operators film and time it themselves, choose the trial, and own the sheet. Team not buying in? The People Whisperer mentoring can help: ci-ai-fusion.netlify.app/lead-the-change/#people-whisperer

5  ELEVATOR SPEECH   30 seconds or less, 3 parts

“We're changing how we do changeovers on Line 2 so that every shift gets more run time with less rushing. We'll get there in 4 steps: measure today's changeover together, trial a better sequence, check the results, then lock it in as standard work. By 30 June you'll see changeovers at 25 minutes or less.”

6  FIRST ACTION TODAY   Same as Houston step 5: one thing today, then log it in your Wins Log

Ask the night shift lead for 10 minutes at tomorrow's huddle to explain the idea and ask what slows changeovers down. By when: ____________ Logged in Wins Log: ☐

Free resource from CI-AI Fusion Ltd · Lead the Change · ci-ai-fusion.netlify.app/lead-the-change/#work-backwards · Pairs with the Houston method worksheet (first action) and the Excel tracker.